# NFH-Kuza-Google Pilot — High-Level Implementation Plan

Eight phases from mobilisation to pilot stabilisation

Kuza Delivery Team

April 2026

Table of Contents

# NFH-Kuza-Google Pilot — High-Level Implementation Plan

Version: 1.0
Date: April 2026
Status: Draft for review

## Introduction

This document sets out the high-level implementation plan for the NFH-Kuza-Google pilot. The pilot delivers a unified, domain-agnostic service-orchestration platform for rural households in Kenya. It spans two Beckn domains — local-services (agri / rural) and health-services — sharing a single Flow Engine, channel layer, data foundation, and integrations with Google Cloud services and the Beckn network.

The plan is organised into eight phases. Each phase has:

- a single Goal statement,

- a list of Inputs Required — named operational artifacts (lists, datasets, content, credentials, decisions) that must be provided before the phase can start, with the provider of each artifact identified, and

- a set of Expected Outputs — concrete deliverables produced by the phase.

The intent of this document is to surface every input that the pilot team needs from partners and from internal teams. Once the high-level plan is reviewed and approved, a detailed plan per phase will follow, breaking each phase into tasks, owners, and durations.

## Phase Summary

| # | Phase | One-line Goal |
| --- | --- | --- |
| 0 | Project Mobilisation | Governance + environments |
| 1 | Foundation — Data Model & Master Data | Schema, seeds, data dictionary |
| 2 | Beckn Network Onboarding | ONIX running, BAP/BPP registered |
| 3 | Core Platform Services | Flow Engine + BAP + BPP running |
| 4 | Channel Integration | WhatsApp Flow Handlers, Web App, Google AI live |
| 5 | Vertical Rollout — Local Services | 4 agri/rural flows live |
| 6 | Vertical Rollout — Health Services | 6 health flows live, cascades + batches |
| 7 | Pilot Launch | Real cohort on the system |
| 8 | Stabilisation & Analytics | KPIs, dashboards, feedback loop |

Sequencing notes:

- Phase 0 unblocks everything else.

- Phases 1 and 2 can run in parallel once Phase 0 is complete.

- Phase 3 depends on Phases 1 and 2.

- Phase 4 depends on Phase 3.

- Phases 5 and 6 default to sequential (Local Services first, then Health Services), though they can parallelise if two independent squads are available.

- Phase 7 is gated by Phase 5 and Phase 6 (whichever subset is in scope for launch).

- Phase 8 begins with pilot go-live and runs continuously thereafter.

## Phase 0: Project Mobilisation

### Goal

Establish governance, environments, and shared understanding before any code is written.

### Inputs Required

| Input | Type | Provider |
| --- | --- | --- |
| Pilot Charter (scope, timeline, budget, success criteria) | Document | Kuza + Google + Beckn jointly |
| Delivery Team Roster (names, roles, time commitments) | List | All partners |
| Steering Committee Members & Cadence | List + schedule | Partners |
| GCP Billing Account ID & owner approval | Credential | Google / Kuza |
| GCP Project Naming Convention (dev / staging / pilot) | Decision | Kuza tech lead |
| GitHub Org + Repo Naming Convention | Decision | Kuza tech lead |
| WhatsApp Business Account approval | Account | Meta (via Kuza) |
| Beckn Fabric Testnet subscriber-registration approval | Account | Beckn |
| Communication tooling (Slack / email channels, doc store) | Setup | Kuza |
| Decision Log Template | Template | Kuza |

### Expected Outputs

- GCP projects provisioned (dev, staging, pilot)

- Shared Git repositories with branching strategy and CI scaffolding

- Secrets management configured (GCP Secret Manager)

- Decision log live for open items (e.g., PostgreSQL migration timing, monitoring stack)

- RACI matrix for the delivery team

## Phase 1: Foundation — Data Model & Master Data

### Goal

Lay down the domain-agnostic data foundation that all subsequent work depends on.

### Inputs Required

| Input | Type | Provider |
| --- | --- | --- |
| Kenya Geography Master List (47 Counties × all Sub-Counties × Wards × known Villages) | Dataset (CSV) | Kuza (existing) or KNBS |
| Top-level Category List per domain | List | Kuza product team |
| Sub-category Taxonomy per top-level category | List per category | Kuza product team + domain SMEs |
| Vertical Catalogue (full list of verticals to support in pilot, with vertical codes) | List | Kuza |
| verticalAttributes Field Definitions per vertical | Per-vertical doc | Domain SMEs |
| Outcome-Type Dictionary per vertical (e.g., TB: TB_POSITIVE, TB_NEGATIVE, CURED, LOST, DIED) | List per vertical | Domain SMEs |
| Capability Vocabulary List (GeneXpert, X-ray, Spirometry, Vet, Vaccination, Brooding, …) | List | Kuza + health partner |
| Role Definitions Dictionary (Seeker, Facilitator, Provider, Coordinator, Validator, Sponsor + sub-roles) | List | Kuza |
| Service Status Lifecycle Enum (NEED_REGISTERED → CLOSED + branches) | Confirmation | From /unified spec |
| Currency + Language Codes Supported in Pilot | Decision | Kuza |
| Master Data Sign-off Matrix (who approves each list) | Matrix | Kuza PM |

### Expected Outputs

- ERD and DDL for new marketplace tables (seeker profile, facilitator profile, provider profile, flow/order, status history, batch, payment, feedback, consent, audit)

- Master-data seed scripts (Kenya geography, category / sub-category taxonomy, role definitions, outcome-type dictionaries per vertical)

- Migration strategy document (MySQL → future PostgreSQL)

- Data-dictionary site or Confluence page

- No application code yet — schema, seeds, and documentation only

## Phase 2: Beckn Network Onboarding

### Goal

Get Kuza recognised as a BAP and a BPP on the Beckn testnet (and later production) networks.

### Inputs Required

| Input | Type | Provider |
| --- | --- | --- |
| Beckn Testnet Subscriber Registration approval | Account | Beckn |
| Production-Network Subscriber Registration approval | Account | Beckn (later) |
| Public Domain Names (e.g., bap-pilot.kuza.one, bpp-pilot.kuza.one) | DNS records | Kuza |
| TLS Certificates for above domains | Certificates | Kuza (via Let’s Encrypt or GCP-managed) |
| Subscriber IDs (one for BAP, one for BPP) — naming approved by network | Decision | Kuza + Beckn |
| Ed25519 Key Pairs for BAP and BPP | Generated keys | Kuza (procedure documented) |
| Network ID Assignment (e.g., kuza-pilot.beckn.one/testnet) | Decision | Beckn |
| Schema Hosting URLs for the 4 generic schemas | URLs | Kuza |
| ONIX Adapter Image Version (which release of fidedocker/onix-adapter to use) | Decision | Kuza tech lead |
| ONIX Routing YAMLs (BAPCaller, BAPReceiver, BPPCaller, BPPReceiver) | Config files | Kuza |
| Discovery Service Endpoint URL | URL | Beckn Fabric |
| Catalog Service Endpoint URL | URL | Beckn Fabric |
| DeDi Registry Endpoint URL | URL | Beckn Fabric |

### Expected Outputs

- ONIX-BAP and ONIX-BPP deployed on GCP (Docker on Cloud Run or GKE)

- BAP and BPP registered on DeDi Registry testnet with keys, callback URIs, subscriber IDs

- 4 generic extension schemas registered with Beckn Catalog Service

- Signed request / verified response working end-to-end in testnet (manual Postman-driven ping crossing the network)

- Operational runbook for registry and ONIX

## Phase 3: Core Platform Services

### Goal

Build the Flow Engine, BAP, and BPP — the platform “heart”.

### Inputs Required

| Input | Type | Provider |
| --- | --- | --- |
| Phase 1 outputs (data model live) | Dependency | Kuza |
| Phase 2 outputs (ONIX deployed and registered) | Dependency | Kuza |
| Flow Template Spec — YAML schema for declaring a flow template | Decision | Kuza tech lead |
| Initial Flow Templates List (which templates needed for pilot, naming convention) | List | Kuza product team |
| Cascade Rules Catalogue (which outcome triggers which cascade — text spec) | List per vertical | Kuza + domain SMEs |
| Batch Rules Catalogue (when batches are created, who can close them) | List | Kuza product team |
| SLA Targets (max latency for discover / confirm; max queue depth) | Decision | Kuza tech lead |
| Capacity Sizing Estimate (peak concurrent flows for pilot) | Estimate | Kuza ops |
| Internal API Naming Convention (Channel Handler ↔ Flow Engine ↔ BAP / BPP) | Decision | Kuza tech lead |
| Logging / Observability Standard (log format, trace IDs, metrics taxonomy) | Decision | Kuza tech lead |

### Expected Outputs

- Flow Engine service: 7-step state machine, flow-template loader, initiation-mode handling, cascade logic, batch management

- BAP service: receives requests from Channel Handlers, constructs Beckn messages, handles async callbacks

- BPP service: receives Beckn messages from ONIX, queries platform for provider catalog, constructs responses

- Unit tests for state transitions, cascade rules, batch lifecycle

- Internal API contracts (Channel → Flow Engine → BAP; Platform → BPP)

- Flow Engine admin tool (read-only, for support / ops)

## Phase 4: Channel Integration — WhatsApp, Web App, Google AI

### Goal

Connect the platform to the user-facing surfaces (WhatsApp, Provider Web App, Google AI).

### Inputs Required

| Input | Type | Provider |
| --- | --- | --- |
| WhatsApp Business Account ID + API token | Credential | Kuza (Meta-issued) |
| Trigger Word List (which words / phrases route to which handler) | List | Kuza product team |
| Read-only access to existing webhook.php source | Repo access | Kuza platform team |
| WhatsApp Outbound Template Content — drafted in EN + SW for each notification scenario | Content (table) | Kuza product team + content writer |
| WhatsApp Template Approval from Meta (per template) | Approval | Meta (via Kuza) |
| Provider Web App UI Mockups (catalog mgmt, order list, order detail, batch view, profile) | Mockups | Kuza UX |
| Brand Assets (logo, colour palette, typography, iconography) | Asset bundle | Kuza brand team |
| Web App Authentication Mechanism (WhatsApp link with token / OTP / phone-based) | Decision | Kuza product + security |
| Google Content API Endpoint URLs + credentials | Credentials + URLs | Google |
| Google AI Interface (Vertex AI / Gemini) credentials + model selection | Credentials + decision | Google + Kuza tech lead |
| Location Normalisation Acceptance Criteria (when does AI output get auto-confirmed vs ask user) | Decision | Kuza product team |
| Messaging Queue Tooling Decision (Pub/Sub vs Cloud Tasks vs cron) | Decision | Kuza tech lead |
| Provider Notification SLA (how fast after order confirmed) | Decision | Kuza product team |

### Expected Outputs

- Channel Webhook router (PHP module in the existing platform) with trigger-word / message-ID-based branching

- Domain-specific Flow Handlers (Local Services handler, Health Services handler) — PHP modules, each consuming Flow Engine APIs

- Provider outbound notification worker (messaging queue + cron) decoupled from the inbound webhook

- Kuza Web App v1 — responsive, no native install — with:

  - Provider onboarding and catalog management

  - Order / flow inbox + details views

  - Role-specific views (Facilitator / Provider / Coordinator)

- Google AI integration library: location normalisation (from Channel Webhook), Content API adapter (from BPP for Advisory)

- WhatsApp template library (registered with Meta) for all outbound patterns

## Phase 5: Vertical Rollout — Local Services Domain

### Goal

Ship the 4 local-services flows end-to-end, covering the SEEKER_INITIATED pattern.

### Inputs Required

| Input | Type | Provider |
| --- | --- | --- |
| Provider Onboarding List — agripreneurs (name, phone, type, service area, services offered, pricing, capacity, availability) | Dataset (CSV per provider type) | Kuza field team |
| Service Catalog Per Provider (services this provider sells, at what unit prices) | Dataset | Kuza field team |
| Service Area Mapping (which provider serves which county / sub-county) | Dataset | Kuza field team |
| Buyer / Aggregator List for Market-Produce (name, location, what they buy, buying prices, collection mode) | Dataset | Kuza field team |
| Vertical Configuration per local-services vertical (default values, dropdown content) | Per-vertical config | Kuza product team |
| Predefined Feedback Options Lists (per category) | Lists | Kuza product team |
| Cancellation Policy Defaults per vertical (window hours, reasons enum) | Decision per vertical | Kuza product team |
| Sample Seeker (Farmer) Profile Set (≥10 test farmers across pilot geography) | Dataset | Kuza field team |
| Vertical-Specific WhatsApp Conversation Scripts (numbered text + button labels in EN + SW) | Per-vertical script | Kuza product team + content writer |
| Test Cases Per Vertical (happy-path + edge cases) | Test plan | Kuza QA |

### Expected Outputs

- Flow templates defined (YAML / config) for each vertical:

  - agri-livelihood-poultry (vaccination, feed, brooding, incubation, etc.)

  - household-education, household-health

  - market-livestock-products (reversed economics)

  - advisory-agri

- verticalAttributes schemas documented per vertical

- Vertical-specific flow-handler logic in the Local Services Flow Handler

- WhatsApp message content (farmer conversations, provider notifications)

- End-to-end integration tests per vertical

- Pilot-ready for the 4 local-services flows

## Phase 6: Vertical Rollout — Health Services Domain

### Goal

Ship the health flows, introducing the PROVIDER_INITIATED, SYSTEM_INITIATED, cascade, and batch primitives.

### Inputs Required

| Input | Type | Provider |
| --- | --- | --- |
| Health Facility Master List (name, type, location, capabilities, operating hours, credential ID) | Dataset (CSV) | Health partner / disease-programme |
| Facility Capability Tags per Facility (GeneXpert, X-ray, Spirometry, DRTB-certified, etc.) | Mapping | Health partner |
| CHP Roster (name, phone, assigned villages / sub-county, credential ID, supervisor) | Dataset | Health partner |
| SCTLC / CTLC Roster (name, phone, assigned geography, supervisor, payment-claim ID) | Dataset | Health partner |
| Clinical Staff Roster per Facility (clinician, nurse, lab, pharmacy — name, role, credential) | Dataset | Health partner |
| Disease-Programme Register Integration Credentials (read + write API access) | Credentials + endpoint URLs | Health partner |
| Patient UUID Generation / Reconciliation Rules (how UUIDs map to register IDs) | Decision | Health partner + Kuza |
| Symptom-Screening Checklist Content (questions, scoring rules) per disease | Per-disease content | Health partner clinical team |
| Contact-Tracing Rules — which contact relationships trigger cascades, exposure window defaults | Rules per disease | Health partner clinical team |
| Cascade Triggers per Outcome (e.g., TB_POSITIVE → which cascades fire) | Mapping | Health partner + Kuza |
| Outbound Notification Templates for Passive Seekers (contact-tracing, post-TB recall) — EN + SW + content-team-reviewed for stigma mitigation | Content | Kuza content + health-partner sign-off |
| Consent Text Content (DPDP / data-sharing wording) — EN + SW | Content | Health partner legal + content writer |
| Campaign Plan Templates (CTLC’s view of how to plan an ACF campaign) | Template | Kuza product + health partner |
| Clinical SLAs (lab turnaround, follow-up windows) | Per-disease decisions | Health partner |
| Test Cases per Health Vertical including cascade scenarios | Test plan | Kuza QA + health-partner clinical reviewer |

### Expected Outputs

- Flow templates for each health vertical:

  - health-tb-screening (CHP-facilitated primary path)

  - health-tb-acf (campaign-style)

  - health-tb-contact-tracing (cascaded)

  - health-tb-treatment

  - health-tb-supervision

  - advisory-health-tb

- CHP-specific Web App views (batch start / close, household visit list, symptom checklist, referral creation)

- Cascade engine rules loaded (positive TB → treatment flow + contact-tracing batch)

- Batch-management UI (CHP daily batch, CTLC campaign batch)

- Outbound WhatsApp notification templates for passive seekers

- Disease-programme register bidirectional sync (read on discover, write on record)

- End-to-end integration tests per flow, including cascade scenarios

- Pilot-ready for the 6 health-services flows

## Phase 7: Pilot Launch

### Goal

Put real households, facilitators, and providers on the system.

### Inputs Required

| Input | Type | Provider |
| --- | --- | --- |
| Pilot Geography Confirmation (which Counties + Sub-Counties for go-live) | Decision | Steering Committee |
| Pilot Cohort Targets (N farmers, N households, N CHPs, N facilities, N agripreneurs) | Number per category | Steering Committee |
| Onboarding Schedule (per cohort, by date) | Calendar | Kuza pilot manager |
| Training Material — Facilitator Guide | Document (slide deck + quick-reference) | Kuza training team |
| Training Material — Provider Guide | Document | Kuza training team |
| Training Material — Coordinator Guide | Document | Kuza training team |
| Training Trainer Roster (who delivers training, where, when) | List + schedule | Kuza pilot manager |
| Support Team Roster + Escalation Path | List | Kuza pilot manager |
| Go / No-Go Checklist (sign-offs needed before launch) | Checklist | Kuza PM |
| Pilot Communication Plan (announcements, partner messaging, expectation-setting) | Plan | Kuza + partners |
| Monitoring Dashboard URLs (for ops visibility on day 1) | URLs | Kuza ops |
| Incident Response Playbook | Playbook | Kuza ops |

### Expected Outputs

- Training completed for Facilitators, Providers, Coordinators

- Providers onboarded with catalog (services, pricing, service areas, capabilities)

- Farmers / households registered (Seeker profiles)

- Monitoring dashboards live (flow volumes, error rates, latency)

- Support channel active (WhatsApp / phone) for early-user issues

- Go-live communication sent to pilot cohort

- First live flows executed and closed end-to-end across all domains

## Phase 8: Stabilisation & Analytics

### Goal

Move from “it works” to “we know how well it works and can improve it.”

### Inputs Required

| Input | Type | Provider |
| --- | --- | --- |
| KPI List with Definitions (conversion rate, lead time, outcome distribution per vertical, etc.) | Document | Kuza product team |
| Pilot Evaluation Criteria (what defines pilot success) | Document | Steering Committee |
| Analytics Tooling Decision (Looker / Data Studio / custom) | Decision | Kuza tech lead |
| Data Access Roles (who sees what) | Matrix | Kuza + partners |
| Reporting Cadence (weekly ops report, monthly steering report) | Schedule | Kuza PM |
| Feedback Collection Mechanism for Pilot Users | Decision (survey / interview / in-app) | Kuza product team |

### Expected Outputs

- Descriptive analytics dashboards (Phase 1 of the Analytics Roadmap): flow conversion funnels, provider performance, facilitator productivity, outcome rates per vertical, geographic heat-maps

- Data-quality monitoring (completeness, referential integrity, cascade closure rates)

- Operational KPIs defined and tracked

- Feedback loop into product backlog (what to fix, what to extend)

- Foundation laid for later predictive and surveillance analytics (not built yet — data is being collected correctly)

## Critical-Path Items

Inputs that most often delay pilots of this shape. Flagging them here so owners can start these earlier than the phase in which they are strictly required:

- Master-data lists (Phase 1) — geography is usually fine; vertical taxonomies and sub-categories can stall waiting on SMEs. Start SME conversations during Phase 0.

- WhatsApp template approvals (Phase 4) — Meta’s approval can take days per template; batch-submit templates early, even if Phase 4 has not formally begun.

- Facility capability + CHP roster data (Phase 6) — these usually live in spreadsheets across partner organisations and need reconciliation. Kick off data-cleanup with the health partner during Phases 1–2.

- Predefined feedback-option lists per vertical (Phase 5) — easy to defer, hard to retrofit. Capture these during Phase 1 master-data work if possible.

- Cascade trigger rules (Phase 6) — require clinical sign-off and often get stuck in review. Start clinical review conversations during Phase 3 even though the rules are consumed in Phase 6.

## Next Steps

- Review this high-level plan with the steering committee.

- Confirm phase ordering, scope, and the critical-path items.

- Upon sign-off, move to detailed planning, breaking each phase into tasks, owners, durations, and dependencies (task-level Gantt / programme plan).

- In parallel, kick off the critical-path items flagged above so they do not block the phases in which they are formally required.

End of document.